## QA & Testing
Pre-Alpha 7/20/25 (Week 3) | Alpha 7/27/25(Week 4) | Beta 8/3/25 (Week 5) | Final Release 8/10/25 (Week 6)
Completed: | Completed: | Completed: | Completed:
Player Character and Movement | Textured environment | Three Functioning enemy AI | Fully functional game
Starter Level Design with two rooms | Two functioning enemy AI | All menu UI functionality | Fully textured environment
One functioning enemy AI | Sound functionality | Level design with 5 rooms
Working Health bar | Start Menu | Textured environment
Player Camera Movement | Win Lose Conditions | Sound functionality
Pause Menu | Level Design with four rooms | Virus reproduction
One functional weapon | Replay functionality | Mini Map
lose screen | Elevators(Must include 4, 2 up and down and side to side)
Win screen | Player pick ups(9 total;at least 3 unique items)
Function Testing: | Function Testing: | Function Testing: | Function Testing:
Game launches | Game launches | Game launches | Full regression testing
Player can look around | Player controls | Player controls
Player can move | Pause Game | Pause game
Pause game | Main Menu | Main menu
Enemy damages player | Enemies damage player | Enemies damage player
Player damages enemy | Player damages enemy | Player damages enemies
lose screen functioning | Win Screen | Win Screen
win screen functioning | Lose Screen | Lose Screen
Player can explore two rooms | Functioning win condition | player can explore 5 rooms
| Can hear sound | No visible untextured area
| Can replay game | can hear sound
| elevators function | enemies reproduce
| pick ups function | Functioning minimap
Player can explore four rooms
No major bugs