## Traceability Matrix
Traceability Matrix
Prototype Title: | "Virus Hunting"
Scope: | First Person Simulation of a player fighting viruses within the body.
Bitbucket Repository Link: | https://github.com/jwellman1307/GAM305_Team_One_FPS.git
Class | Functionality | Implementation Description | Program | Begin Phase | Complete Phase | Assigned to | Completed? Y/N | Notes
Player Character | Player Movement | Player character wasd and camera movement | Unreal Engine 5.6 | Pre-Alpha | Alpha | Ryan - Programmer | Y
Weapon | Projectiles | Functionality for projectiles for weapon | Unreal Engine 5.6 | Pre-Alpha | Alpha | Ryan - Programmer | N
Spider Enemy | AI Behavior Tree | Enemy AI | Unreal Engine 5.6 | Alpha | Beta | Travis - UI/Programmer
Spawner Enemy | AI Behavior Tree | Enemy AI. Spawns enemies | Unreal Engine 5.6 | Alpha | Beta | Travis - UI/Programmer
Parasite Enemy | AI Behavior Tree | Enemy Ai. | Unreal Engine 5.6 | Pre-Alpha | Alpha | Travis - UI/Programmer | N
MiniMap | Map Display in Hub |  | Unreal Engine 5.6 | Alpha | Beta | Travis - UI/Programmer
Pickup Item | Items for boosts | 9 total items; at least 3 unique items | Unreal Engine 5.6 | Pre-Alpha | Alpha | Ryan - Programmer | N
Elevators | Movement between Levels | 4 elevators. Two going up and down. Two going side to side. | Unreal Engine 5.6 | Pre-Alpha | Alpha | Ryan - Programmer | N
Menus | Pause/Retry/Win&Lose |  | Unreal Engine 5.6 | Pre-Alpha | Beta | Travis - UI/Programmer | N
Level Design | Layout of Level | Five rooms total. Stacked rooms with elevators | Unreal Engine 5.6 | Pre-Alpha | Beta | Ethan - Level Designer | N
Player Character | Asset |  | Unreal Engine 5.6 | Pre-Alpha | Pre-Alpha | Sarah - Artist | N
Weapon & Projectile | Asset |  | Unreal Engine 5.6 | Pre-Alpha | Pre-Alpha | Sarah - Artist | Y
Spider Enemy | Asset |  | Unreal Engine 5.6 | Pre-Alpha | Pre-Alpha | Sarah - Artist | N
Spawner Enemy | Asset |  | Unreal Engine 5.6 | Pre-Alpha | Pre-Alpha | Sarah - Artist | N
Parasite Enemy | Asset |  | Unreal Engine 5.6 | Pre-Alpha | Pre-Alpha | Sarah - Artist | Y

## PreAlphaTest Plan
Test Plan
Bitbucket Repository Link: | [https://github.com/jwellman1307/GAM305_Team_One_FPS.git]
Test Feature | Description of Test | Pass/Fail | Bugs | Runtime Errors | Updates/Error Resolution
Level Start | The level loads in when the game starts
Player character Movement | Player can move around on the map
Player camera | Player can visually look around smoothly
Pause game | Player can pause the game
Enemy AI | Enemy AI is functioning by attacking the player in range
Functioning Player Health Bar | Players receives damage when attacked by enemy
Functioning Enemy Health | Enemy received damage when attached by player
Lose screen functions | The lose screen appears when player health reaches zero
Win screen functions | The win screen appears when player reaches an amount of kills
Two rooms | Player can explore two rooms

## AlphaTestPlan
Test Plan
Bitbucket Repository Link: | [https://github.com/jwellman1307/GAM305_Team_One_FPS.git]
Test Feature | Description of Test | Pass/Fail | Bugs | Runtime Errors | Updates/Error Resolution
Level Start | The level loads in when the game starts
Player character Movement | Player can move around on the map
Player camera | Player can visually look around smoothly
Pause game | Player can pause the game
Enemy AI | Enemy AI is functioning by attacking the player in range
Functioning Player Health Bar | Players receives damage when attacked by enemy
Functioning Enemy Health | Enemy received damage when attached by player
Lose screen functions | The lose screen appears when player health reaches zero
Win screen functions | The win screen appears when player reaches an amount of kills
Four rooms | Player can explore four rooms
Replay | Player can replay the game on win or lose condition
Elevator(up and down) | Player can get on an elevator that moves up and down
Elevator (side to side) | Player can get on an elevator that moves from side to side
Player pick up items | Have all three items function when the player picks it up

## BetaTestPlan
Test Plan
Bitbucket Repository Link: | [https://github.com/jwellman1307/GAM305_Team_One_FPS.git]
Test Feature | Description of Test | Pass/Fail | Bugs | Runtime Errors | Updates/Error Resolution
Level Start | The level loads in when the game starts
Player character Movement | Player can move around on the map
Player camera | Player can visually look around smoothly
Pause game | Player can pause the game
Enemy AI | Enemy AI is functioning by attacking the player in range
Functioning Player Health Bar | Players receives damage when attacked by enemy
Functioning Enemy Health | Enemy received damage when attached by player
Lose screen functions | The lose screen appears when player health reaches zero
Win screen functions | The win screen appears when player reaches an amount of kills
Five rooms | Player can explore five rooms
Replay | Player can replay the game on win or lose condition
Elevator(up and down) | Player can get on an elevator that moves up and down
Elevator (side to side) | Player can get on an elevator that moves from side to side
Player pick up items | Have all three items function when the player picks it up
No visable untextured area | Check for areas not textured on the map
Sound Functionality | Player can hear sound when performing tasks
Enemy Reproduction | Enemies can reproduce
Minimap | Minimap functions as intended

## FinalRelease
Test Plan
Bitbucket Repository Link: | [https://github.com/jwellman1307/GAM305_Team_One_FPS.git]
Test Feature | Description of Test | Pass/Fail | Bugs | Runtime Errors | Updates/Error Resolution
Level Start | The level loads in when the game starts
Player character Movement | Player can move around on the map
Player camera | Player can visually look around smoothly
Pause game | Player can pause the game
Enemy AI | Enemy AI is functioning by attacking the player in range
Functioning Player Health Bar | Players receives damage when attacked by enemy
Functioning Enemy Health | Enemy received damage when attached by player
Lose screen functions | The lose screen appears when player health reaches zero
Win screen functions | The win screen appears when player reaches an amount of kills
Five rooms | Player can explore five rooms
Replay | Player can replay the game on win or lose condition
Elevator(up and down) | Player can get on an elevator that moves up and down
Elevator (side to side) | Player can get on an elevator that moves from side to side
Player pick up items | Have all three items function when the player picks it up
No visable untextured area | Check for areas not textured on the map
Sound Functionality | Player can hear sound when performing tasks
Enemy Reproduction | Enemies can reproduce
Minimap | Minimap functions as intended