## Traceability Matrix
Traceability Matrix
Prototype Title: | "Virus Hunting"
Scope: | First Person Simulation of a player fighting viruses within the body.
Bitbucket Repository Link: | https://github.com/jwellman1307/GAM305_Team_One_FPS.git
Class | Functionality | Implementation Description | Program | Begin Phase | Complete Phase | Assigned to | Completed? Y/N | Notes
Player Character | Player Movement | Player character wasd and camera movement | Unreal Engine 5.6 | Alpha | Alpha | Ryan - Programmer | Y | Still needs reload animation, basic animations
Weapon | Projectiles | Functionality for projectiles for weapon | Unreal Engine 5.6 | Alpha | Alpha | Ryan - Programmer | Y
Spider Enemy | AI Behavior Tree | Enemy AI | Unreal Engine 5.6 | Alpha | Beta | Travis - UI/Programmer
Spawner Enemy | AI Behavior Tree | Enemy AI. Spawns enemies | Unreal Engine 5.6 | Alpha | Beta | Travis - UI/Programmer
Parasite Enemy | AI Behavior Tree | Enemy Ai. | Unreal Engine 5.6 | Alpha | Alpha | Travis - UI/Programmer | N
MiniMap | Map Display in Hub |  | Unreal Engine 5.6 | Alpha | Beta | Travis - UI/Programmer
Pickup Item | Items for boosts | 9 total items; at least 3 unique items | Unreal Engine 5.6 | Alpha | Alpha | Ryan - Programmer | N
Elevators | Movement between Levels | 4 elevators. Two going up and down. Two going side to side. | Unreal Engine 5.6 | Alpha | Alpha | Ryan - Programmer | N
Menus | Pause/Retry/Win&Lose |  | Unreal Engine 5.6 | Alpha | Beta | Travis - UI/Programmer | N
Level Design | Layout of Level | Five rooms total. Stacked rooms with elevators | Unreal Engine 5.6 | Alpha | Beta | Ethan - Level Designer | N
Player Character | Asset |  | Unreal Engine 5.6 | Pre-Alpha | Pre-Alpha | Sarah - Artist | N
Weapon & Projectile | Asset |  | Unreal Engine 5.6 | Pre-Alpha | Pre-Alpha | Sarah - Artist | Y
Spider Enemy | Asset |  | Unreal Engine 5.6 | Pre-Alpha | Pre-Alpha | Sarah - Artist | N
Spawner Enemy | Asset |  | Unreal Engine 5.6 | Pre-Alpha | Pre-Alpha | Sarah - Artist | N
Parasite Enemy | Asset |  | Unreal Engine 5.6 | Pre-Alpha | Pre-Alpha | Sarah - Artist | Y

## AlphaTestPlan
Test Plan
Bitbucket Repository Link: | [https://github.com/jwellman1307/GAM305_Team_One_FPS.git]
Test Feature | Description of Test | Pass/Fail | Bugs | Runtime Errors | Updates/Error Resolution
Level Start | The level loads in when the game starts
Player character Movement(WASD) | Player can move around on the map
Player camera | Player can visually look around smoothly
Worm enemy can damage | Worm enemy can damage player
Worm enemy take damage | Worm enemy AI takes damage from player
Worm enemy defeated | Worm enemy can be defeated
Spider enemy can damage | Spider enemy can damage the player
Spider enemy take damage | Spider enemy can take damage from the player
Spider enemy defeated | Spider enemy can be defeated
Healthbar takes damage | Healthbar is visible and goes down when player takes damage
Main Menu | Player can interact with the main menu
Pause Menu | Player can bring up and interact | Yes
Win Screen | Activates when player wins | Yes | Win state set up just without actual condition
Lose Screen | Activates when player loses | Yes
Replay | Player can interact | yes
Sound | Can hear some sound quality | Yes | Still making adjustments
Elevators(Up and down) | Elevators function when player steps on platfor | Yes
Elevators(Side to side) | Elevators function when player steps on platform | No | Quick adjustment
Pick up items | Player can up pick up three unique items | Yes | Needs asset builds replaced
Collision | Proper collision | yes | making adjustments along the way
Shooting | Player can shoot | yes
Rooms | Player can access and explore at least four rooms | yes

## BetaTestPlan
Test Plan
Bitbucket Repository Link: | [https://github.com/jwellman1307/GAM305_Team_One_FPS.git]
Test Feature | Description of Test | Pass/Fail | Bugs | Runtime Errors | Updates/Error Resolution
Level Start | The level loads in when the game starts
Player character Movement(WASD) | Player can move around on the map
Player camera | Player can visually look around smoothly
Worm enemy can damage | Worm enemy can damage player
Worm enemy take damage | Worm enemy AI takes damage from player
Worm enemy defeated | Worm enemy can be defeated
Spider enemy can damage | Spider enemy can damage the player
Spider enemy take damage | Spider enemy can take damage from the player
Spider enemy defeated | Spider enemy can be defeated
Spawner enemy can damage | Spawner enemy can damage the player
Spawner enemy take damage | Spawner enemy can take damage from player
Spawner enemy defeated | Spawner enemy can be defeated
Spawner enemy reproduction | Spawner enemy reproduces additional viruses
Spawner viruses can damage | Spawner viruses can damage the player
Spawner viruses take damage | Spawner viruses can take damage from the player
Spawner viruses defeated | Spawner viruses can be defeated
Healthbar takes damage | Healthbar is visible and goes down when player takes damage
Main Menu | Player can interact with the main menu
Pause Menu | Player can bring up and interact
Win Screen | Activates when player wins
Lose Screen | Activates when player loses
Replay | Player can interact
Sound | Can hear some sound quality
Elevators(Up and down) | Elevators function when player steps on platfor
Elevators(Side to side) | Elevators function when player steps on platform
Pick up items | Player can up pick up three unique items
Collision | Proper collision
Shooting | Player can shoot
Rooms | Player can access and explore at least five rooms
Minimap | Functioning minimap

## FinalTestPlan
Test Plan
Bitbucket Repository Link: | [https://github.com/jwellman1307/GAM305_Team_One_FPS.git]
Test Feature | Description of Test | Pass/Fail | Bugs | Runtime Errors | Updates/Error Resolution
Level Start | The level loads in when the game starts
Player character Movement(WASD) | Player can move around on the map
Player camera | Player can visually look around smoothly
Worm enemy can damage | Worm enemy can damage player
Worm enemy take damage | Worm enemy AI takes damage from player
Worm enemy defeated | Worm enemy can be defeated
Spider enemy can damage | Spider enemy can damage the player
Spider enemy take damage | Spider enemy can take damage from the player
Spider enemy defeated | Spider enemy can be defeated
Spawner enemy can damage | Spawner enemy can damage the player
Spawner enemy take damage | Spawner enemy can take damage from player
Spawner enemy defeated | Spawner enemy can be defeated
Spawner enemy reproduction | Spawner enemy reproduces additional viruses
Spawner viruses can damage | Spawner viruses can damage the player
Spawner viruses take damage | Spawner viruses can take damage from the player
Spawner viruses defeated | Spawner viruses can be defeated
Healthbar takes damage | Healthbar is visible and goes down when player takes damage
Main Menu | Player can interact with the main menu
Pause Menu | Player can bring up and interact
Win Screen | Activates when player wins
Lose Screen | Activates when player loses
Replay | Player can interact
Sound | Can hear some sound quality
Elevators(Up and down) | Elevators function when player steps on platfor
Elevators(Side to side) | Elevators function when player steps on platform
Pick up items | Player can up pick up three unique items
Collision | Proper collision
Shooting | Player can shoot
Rooms | Player can access and explore at least five rooms
Minimap | Functioning minimap